## Bill No 1
BILL OF QUANTITIES No. 1
PRELIMINARIES AND GENERAL
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
A1 | Contractual Requirements
1.01 | Performance Security | Item | 1
1.02 | Insurance for Works and Contractor's Equipment | Item | 1
1.03 | Insurance against Injury to Third Party Persons and Damage to Property | Item | 1
1.04 | Provision of Workman's Compensation | Item | 1
A2 | Special Requirements
Office for the Engineer
2.01 | Provide a temporary Engineer Staff office including all Associated works to be used during the duration of the construction. The office space shall be as specified the Technical specification and as per the attached drawing appendix 2.1 | Item | 1
Services for the Engineer's Staff
Survey works
2.02 | Provide, fuel, oils, lubricants, servicing/repairs and Comprehensive insurances and maintain with drivers the following according to specifications |  |  |  |  | DAB
(a) | 3No. brand new 4WD fully loaded Station Wagon Vehicle of minimum diesel engine capacity of 2800cc approved by the Engineer for his exclusive use, inclusive of the first 5000km per vehicle month. Vehicles to revert to the Contractor at the end of the project. | Veh. Month | 72 | [5 empty] | 48 | 36
(b) | 1No. brand new 4WD fully loaded double cabin pickups of minimum diesel engine capacity of 2400cc approved by the Engineer for his exclusive use, inclusive of the first 5000km per vehicle month. Vehicle to revert to the Contractor at the end of the project. | Veh. Month | 14
2000000
2.03 | EO Item 2.02(a) and (b) for kilometers travelled in any month in excess of 5,000km for all running costs | Km | 12000
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
2.04 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items 2.02 a) and b) above | %
2.05 | Allow Monthly Sum of KES100,000 per month for 12months for purchasing and provision of Air-time, internet services, courier services, etc. for the Engineer's Office | Month | 12
2.06 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items 2.05 above | %
Equipment for use by the Engineer's office staff
2.07 | Allow a Sum for furnishing and equipping of Engineers Office. To include furniture, laptop computers, digital cameras, printers etc. as per the attached list appendix 2.2 | Item | 1
2.08 | Allow a Sum of KES 200,000 per month for 12 months for monthly maintenance of office equipment, stationery, office consumables, toileteries, payment of water services and electricity supply etc. for use by the Engineer's Staff office | Month | 12
2.09 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items 2.07 and 2.08 above | %
2.1 | Allow for supply of protection and safety equipment and clothing for the use by the Engineer Staff office as Per Technical specifications and as per the attached list appendix 5 | Item | 1
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
Attendance Upon Project Manager's Staff
Provide the following Staff for the Project Engineer's Office. (Note: The Staff to be employed by the Contractor)
2.11 | Chainmen, 4No. | Month | 12
2.12 | Provide and maintain office attendants (4 No.) to carry out general office cleaning, preparation of tea, meals, and other related office support duties | Month | 12
2.13 | Secretary, 1No. | Month | 20
2.14 | Graduate Engineers 2No. | Month | 20
2.15 | Assistant Surveyor 1No. | Month | 12
2.16 | EHS Officer 1No. | Month | 15
Testing of Materials and Works
2.17 | Allow a Sum for all laboratory and field tests required for the Works, including tests on soils, gravel/murram, aggregates, concrete, water, and any other tests as directed by the Engineer | Sample | 300
2.18 | Allow a Sum of KES 5,000,000 per person per trip for Engineer office Staff and Employer's attendance during factory inspection of materials in the manufacturer's factory(5persons). | Trip | 5
2.19 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items 2.17 and 2.18 above | %
Project Sign Boards
2.2 | Provide, erect and maintain for the duration of the contract project two(2) participant sign boards as directed by the Engineer. | No | 2
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
Other Requirements
2.21 | Allow a Sum of KES 50,000 per Km for setting out of the road works and survey, including all topographic survey, provision of benchmarks, reference pegs confirmatory engineering survey as required by the Engineer | Km | 35
2.22 | Allow a provision of instruments, equipment, and all necessary staff as required by the Engineer as per the attached list Appendix 3 | Sum | 1
2.23 | Allow for a sum of KES 200,000 per month for maintainance for the duration of the contract Survey equipment for use by the Engineer's Representative for the entire duration of the contract | Month | 12
2.24 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items 2.22 and 2.23 above | %
2.25 | Allow a sum for preparation of working drawings (Cross-Sections at 20m intervals and drainage structure setting out details) & earthworks computations and As-Built Drawings and delivery of the required copies in both hard and soft format as directed by the Engineer | Nr | 3500
A3 | Method Related Charges
Accommodation and Buildings
3.01 | Establishment and maintenance of Contractor's camps, offices, facilities, etc. and provision of all equipment that will be required during the entire contract period and removal and demobilization after completion of the project | Month | 24
3.02 | Allow for KES 200,000 per month for Provision for monthly office consumables like tea,Lunch, water, etc for the Engineer's Office | Month | 12
3.03 | Allow for KES 100,000 per month for provision of refreshments during monthly progressive site meetings as may be required and directed by the Engineer | Month | 12
3.04 | Allow for provision for Engineer’s Accommodation (fully furnished and serviced) according to the specification and engineer’s approval | Month | 20
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
3.05 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items 3.02, 3.03 and 3.04 above | %
3.06 | Allow for Provision of Adequate Monthly Security for the Engineer's office | Month | 12
3.07 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items 3.06 above | %
100000
Relocation of services
3.08 | Provisional Sum KES 10,000,000 for removal, diversion, protection and alteration of existing services, including liaison with relevant authorities, complete as directed by the Engineer. | PS | 1
400000
Knowledge transfer through internship
3.09 | Allow a sum of KES 100,000 per month for internship programme for graduate students stationed in the Engineer's office for the entire project period as part of knowledge transfer programme. | Nr | 20
3.1 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items 3.08 and 3.09 above | %
Dispute Board (DB)
3.11 | Allow a Prime Cost Sum (P.C) of KES 11,700,000 to cover Employer's obligation to pay DB as per the attached list Appendix 4 | P.C | 1
3.12 | E.O. item 3.11 for the contractor's overheads and profits | %
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
Software Provision
3.13 | Provide and implement BIM for the Works, including BEP preparation, coordinated multi-disciplinary modelling, clash detection, drawing production, and submission of federated and as-built models using approved BIM software, complete as specified and as directed by the Engineer. | LS | 1
3.14 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Item 3.13 above | %
Videos and Photographs
3.15 | Provision of photographs showing the progress of the works in accordance with specification | Month | 12
3.16 | The Contractor shall set out below and fully describe and price, in the spaces provided, any temporary work or obligation or anything in the Conditions of Contract or in the Specification not included by him in his rates elsewhere and for which he considers a separate charge is required. The prices inserted shall be considered to be fixed lump sums covering the whole of the work and as such will not be subjected to adjustment for any reason. If the Contractor makes no entry in the space provided then the rates inserted elsewhere in the Bill will be deemed to cover all his obligations under the Contract.
| i). | Sum | 1
| ii). | Sum | 1
| ii). | Sum | 1
| iv). | Sum | 1
| v). | Sum | 1
| vi). | Sum | 1
Sub Total
Total Carried Forward to Summary Page
50000
[7 empty] | 350000 | 29166.6667
29167

## Bill No 4
BILL OF QUANTITIES No. 4
SITE CLEARENCE
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
4.01 | Clear site on road reserve by removal of trees, hedges, bushes, vegetation and other deleterious materials. | m² | 451058
4.02 | Remove top soil to an approved depth upto a maximum of 200mm and stockpile for reuse as directed by the Engineer. | m³ | 90211
Sub Total
Total Carried Forward to Summary Page

## Bill No 5
BILL OF QUANTITIES No. 5 | [5 empty] | 698890
EARTHWORKS
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES |  | 117480000 |  | 105732000
| Note: No separate payment shall be made for gravel for blinding or hauling to spoil unsuitable excavation materials and the cost of such shall be included in the rates and prices |  |  |  |  | 192240 |  |  | 11748000
[6 empty] | 532540 | 213600
5.01 | Fill and compact in Soft Material | m³ | 340300 |  |  | 250398 | 608988 |  |  | 130363.2
[6 empty] | 11748 | 21360
5.02 | Fill in Hard Material | m³ | 34030 |  |  | 45778
5.03 | Cut to Spoil in Soft Material | m³ | 697143 |  |  | 350 | 57672 |  |  | 69145.2
57672
5.04 | Cut to Spoil in Hard Material | m³ | 69714.3 |  |  |  | 754815
[6 empty] | 89901.5581 | 219622
5.05 | Provide process and compact improved subgrade as directed by the Engineer. CBR of not less than 14% measured after a 4-day soak in a laboratory mix compacted to a dry density of 100% MDD (AASHTO T99) and a swell of less than 1%. | m3 | 89902 |  |  |  | 1.2 | 98152.8
[8 empty] | 608988 | 697143
5.06 | Compact the top 150 mm layer below formation level below fills and cuts to 95% MDD (AASHTO T99) | m³ | 8798 |  |  | 180 |  | 340300
5.09 | Excavation in Swamps | m³ | 105 |  |  | 400
5.1 | Plant grass on the slope and inverts of ditches to reduce scour effects, or on slopes to reduce soil erosion and to improve stability. | m² | 960
8178138
Sub Total
Total Carried Forward to Summary Page

## Bill No 7
BILL OF QUANTITIES No. 7
EXCAVATION & FILLING FOR STRUCTURES
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
Note: No separate payments shall be made for gravel for blinding or hauling to spoil unsuitable excavation materials and the cost of such shall be included in the rates and prices
7.01 | Excavate for Structure in Soft Material
| (a) 600mm Dia Concrete Pipe Culverts for access to public institutions | m³ | 126
| (b) 600mm Dia Concrete Pipe Cross culverts | m³ | 726
| (c) 900mm Dia Concrete Pipe Cross Culverts | m³ | 1532
| (d) 1200mm Dia Concrete Pipe Cross Culverts | m³ | 0
7.04 | Extra Over Items (7.01) and (7.02) for Excavation in Hard Material | m³ | 240
7.05 | Selected Granular Fill Material | m³ | 1650
7.07 | Stone Pitching | m² | 9620
7.08 | Gabion Mesh | m² | 9600
7.09 | Rockfill to Gabions | m³ | 1920 |  |  | 960
Sub Total
Total Carried Forward to Summary Page

## Bill No 8
BILL OF QUANTITIES No. 8
CULVERT & DRAINAGE WORKS
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
Note: No separate payments shall be made for gravel for blinding or hauling to spoil unsuitable excavation materials and the cost of such shall be included in the rates and prices
8.12 | Selected Backill Material | m³ | 10
8.14 | Rockfill below Culverts | m³ | 10
8.15 | Provide, Lay and Joint
| (a) 600mm dia Concrete pipe plot access culverts | m | 3000
| (b) 600mm Dia Concrete Pipe Culverts for access to public institutions | m | 105 |  |  | Rate= | 6341.3
| (c) 600mm Dia Concrete Pipe Cross culverts | m | 605
| (d) 900mm Dia Concrete Pipe Cross Culverts | m | 740
| (e) 1200mm Dia Concrete Pipe Cross Culverts | m | 0
8.16 | Concrete Class 15/20 to Beds, Sorrounds and Haunches
| (a) 600mm Dia Concrete Pipe to public institutions access culverts | m³ | 53
| (b) 600mm Dia Concrete Pipe to road junctions culverts | m³ | 303
| (c) 900mm Dia Concrete Pipe Cross Culverts | m³ | 636
| (d) 1200mm Dia Concrete Pipe Cross Culverts | m³ | 0
8.17 | Concrete Class 25/20 to Wingwalls, including reinforcement and formwork
| (a) 600mm Dia Concrete Pipe to public institutions access culverts | m³ | 166
| (b) 600mm Dia Concrete Pipe to road junctions culverts | m³ | 956
| (c) 900mm Dia Concrete Pipe Cross Culverts | m³ | 3012
| (d) 1200mm Dia Concrete Pipe Cross Culverts | m³ | 0
8.18 | Concrete Class 20/20 to Minor Drainage Structures | m³ | 5
8.19 | Concrete Scour Checks Class 20/20 | m³ | 36
Sub Total
Total Carried Forward to Summary Page

## Bill No 9
BILL OF QUANTITIES No. 9
PASSAGE OF TRAFFIC
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
Note: Notwithstanding the provision of Section 9 of the Standard Specification, no extra payments shall be due as all costs shall be deemed to be included in the rates inserted herein
9.01 | Allow for the passage of traffic through and around the works including the provision of road signs and barriers in accordance with the specifications and as directed by the Engineer | Month | 12
9.02 | Grade, water and compact access road to Mwangala primary school ahead of works in accordance with the specifications and as directed by the Engineer(this will be referred as enabling works) | km | 1
Rate=
Sub Total
Total Carried Forward to Summary Page

## Bill No 10
BILL OF QUANTITIES No. 10
GRAVEL WEARING COURSE
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES |  | ROW | [7 empty] | 62919 | 81794.7
[7 empty] | 6m | 9m | 12m | 15m | 17m | 18m
10.1 | Provide, lay natural gravel to carriageway, water and compact to min 95% MDD and CBR not less than 20 | m³ | 81794 |  |  | Total lengths | 1026.177 | 4530.52 | 9696.082 | 8962.331 |  | 6258.551 | 30473.661 |  | 0
[7 empty] | 6 | 9 | 12 | 15 |  | 18 |  |  | 137171250
[7 empty] | 6157.062 | 40774.68 | 116352.984 | 134434.965 | 0 | 112653.918 | 410373.609 |  | 58655
70500
2250000
[6 empty] | SEZ RAP Design- Summary of right of way lengths | [8 empty] | 274342500
[6 empty] | Right of Way (m) | 6 | 9 | 12 | 15 | 18 | 40 |  |  | 274342500
[6 empty] | Sub-Total lengths (m) | 1250.214 | 4625.015 | 9770.343 | 10184.04 | 8065.265 | 78.692 | 33973.569
Total (m)
[6 empty] | Top Soil Stripping | 7501.284 | 41625.135 | 117244.116 | 152760.6 | 145174.77 | 3147.68 |  | 88816.1812
[6 empty] | Carriageway | 5 | 5 | 6 | 8 | 8 | 8
[6 empty] | Top Soil Stripping | 6251.07 | 23125.075 | 58622.058 | 81472.32 | 64522.12 | 629.536 | 58655.5447
[6 empty] | Gravel Wearing Course | SAME AS ABOVE
Sub Total
Total Carried Forward to Summary Page

## Bill No 17
BILL OF QUANTITIES No. 17
CONCRETE WORKS
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
Concrete
17.02 | Provide and place Class 25 (20) reinforced concrete to all structural elements as shown in Drawings | m³ | 49.5 |  |  | 49.5
17.03 | Provide and place concrete class 15 (40) as blinding and backfill to foundations as directed by the Engineer. | m³ | 4.5 |  |  | 4.5
Formwork
17.06 | Formwork for Formed Surface
| a) Vertical formwork class F2 finish | m² | 109 |  |  | 218.5
| b) Horizontal formwork class F2 finish | m² | 109
Reinforcement
17.1 | High Yield Steel Reinforcement
| a) diameter equal to or less than 16mm. | tonne | 2.7 |  |  | 5397
| b) diameter greater than 16 mm. | tonne | 2.7
Sub Total
Total Carried Forward to Summary Page

## Bill No 22
BILL OF QUANTITIES No. 22
DAYWORKS
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
PLANT/EQUIPMENT
(The Contractor's Basic Hire Rates)
22.01 | Truck Flat bed: 2.5 - 5 Tonnes | Hour | 150
22.02 | Truck with crane 4t | Hour | 150
22.03 | Water Tanker: 6000 - 8000 Lt. | Hour | 150
22.04 | Motor Grader (e.g. CAT 112F): 100 - 130 HP | Hour | 150
22.05 | Bulldozer BD65EX | Hour | 150
22.06 | Excavator 130-150hp | Hour | 150
22.07 | Backhoe loader 130-150hp | Hour | 150
22.08 | Pedestrian Roller: 700 - 1000 Kg. | Hour | 150
22.13 | Grass cutter | Hour | 150
22.14 | Vibrator pneumatic/Tamper | Hour | 150
22.15 | Tipper 17tonnes | Hour | 300
22.16 | Wheel loader(3-5tonnes) | Hour | 400
22.17 | Boring machine,81kw | Day | 150
22.18 | Air compressor 150CFM, 4250LPM | Day | 150
22.19 | Concrete mixer 14 Cu. Ft | Day | 150
22.2 | Poker Vibrator(Various Sizes) | Day | 150
22.21 | Water pump complete with engine; 10CM/Hr output | Day | 150
22.22 | Compressor machine with 3 jacks(Rock breaker) | Day | 75
22.23 | Single drum steel Vibrator roller: 9-10T, 130 HP | Hour | 150
A22.24 | Mobile concrete mixers | Day | 30
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
B.22.1 | Labour
B.22.1.1 | Support Staff | M.Day | 1000
B22.1.2 | Unskilled labour | M.Day | 1000
B22.1.3 | Artisans G2 | M.Day | 1000
B22.1.4 | Skilled Labour: Overseer | M.Day | 500
B22.1.5 | Skilled Labour: Operator | M.Day | 400
B22.1.6 | Site Engineer | M.Day | 600
B22.1.7 | Site Surveyor | M.Day | 320
Materials
C.22.1 | Fine aggregates(sand) | t | 1500
C.22.2 | Fine aggregates (stone dust) | t | 1500
C.22.3 | Graded aggregates (ballast) | t | 1500
C.22.4 | Water | m³ | 1000
C.22.5 | Cement (ordinary portland) | t | 700
C.22.6 | Hydrated lime | t | 300
C.22.7 | Reinforcement bars | t | 120
C.22.8 | Culvert Installation with surround - 600mm | m | 3000
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
DAYWORKS SUMMARY
Plant
Labour
Materials
Sub Total
Total Carried Forward to Summary Page

## Bill No23
BILL OF QUANTITIES No. 23
SOLAR STREET LIGHTING
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
(All quantities are subject to remeasurement)
SECTION 2: KPA SECTION (FROM INTERCHANGE TO MAIN PORT GATE)
23.2 | Lighting Columns
49.5
a) 10 meter high tapered octogonal single-section
| 10 Meter Octagonal pole with Bottom Diameter :-155mm (A/F) Top Diameter:- 70mm (A/F), Thickness top to bottom 3mm, Base Plate 260*260*16mm. |  |  |  |  | 4.5
23.3 | i) Single sided arm | No. | 720
| ii)Foundation Bolt:- M24 x 750 mm long x 04 nos. | No. | 720
| iii)Single Arm Bracket | No. | 720
23.4 | Lighting Column Foundation
| Supply and install concrete foundation for lighting columns whose rate must include submission of design calculations, pipe sleeves, reinforcements, high tensile grout, foundation bolts etc. |  |  |  |  | 218.5
| i)10m (H) pole light | No. | 720
23.5 | Solar Luminare
Supply and install and connect the following IP66 LED luminaire c/w LEDs, Solar Panel, LiFePO4 Battery with Baterry Management System, and all mounting accessories and earthing as per specifications and drawings:
a) | Light Module: 1 X 250W LED Solar Street Lantern Luminous efficacy 210lm/W) CCT 4000K, CRI 70, ɳ=84.49%, Luminare Luminous Flux 52,500lm,IP66 c/w control gears, LED driver Programmable. Class I electrical, IP66, IK08. Housing: die-cast aluminium, powder coated textured light grey. Complete with 4000K LED. lifetime 100,000hrs etc. to Philips Lighting or approved equivalent (Provisional) Inscribed (PROPERTY OF KPA).Solar Panel; 18Volts, 180 Watts, high-efficiency monocrystalline ,Battery: 1536 WH, LiFePO4 lithium, >4000 cycles at 80% DOD Solar Charging time; 5-7 hours by bright Sunlight,Light time: 5-6 nights after full charging,Guard Level; IP66,Working Temperature: -250C to 650C,Warranty: 10 years,Photocell Controll+Microwave Motion Sensor Contro+Remote Control+Battery Management System. Auto on/off/sensor.All to be submitted with the specific data sheets and manuals | No. | 419
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
b) | Light Module: 1 X 200W LED Solar Street Lantern Luminous efficacy 210lm/W) CCT 4000K, CRI 70, ɳ=84.49%, Luminare Luminous Flux 21,100lm,IP66 c/w control gears, LED driver Programmable. Class I electrical, IP66, IK08. Housing: die-cast aluminium, powder coated textured light grey. Complete with 4000K LED. lifetime 100,000hrs etc. to Philips Lighting or approved equivalent (Provisional) Inscribed (PROPERTY OF KPA) Solar Panel; 18Volts, 160 Watts, high-efficiency monocrystalline,Battery: 60 AH, LiFePO4 lithium, >4000 cycles at 80% DOD,Solar Charging time; 5-7 hours by bright Sunlight,Light time: 5-6 nights after full charging,Guard Level; IP66,Working Temperature: -250C to 650C,Warranty: 10 years,Photocell Controll+Microwave Motion Sensor Contro+Remote Control+Battery Management System. Auto on/off/sensor.All to be submitted with the specific data sheets and manuals. | No. | 301
23.6 | Earthing
i) | Earthing of every lighting columns to achieve less than 5 ohm in accordance to the specification. | No. | 720
23.7 | Labelling
i) | Labelling of all columns with reflective stickers to 3M or approved equivalent in accordance to the initial and numberings as per drawing. | No. | 720
23.8 | Miscellineous
i) | Submission of shop drawings, samples, catalogues, etc. for approval. | Item | 1
ii) | Factory acceptance test of luminaires at the place of manufacture/assembly including passage, lodging, travelling etc for 6 persons. | Item | 6
iii) | Factory acceptance test of columns at the place of manufacture including passage, lodging, etc for 6 persons. | Item | 6
iv) | Provide Independent laboratory test for light fittings for the following features:- a) Photometrics b) IP rating. The Institution should be an accredited testing, inspection and certification body | Item | 1
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
Testing and Commissioning
Testing and commissioning of the whole street lighting installation by a certified Testing and Commisioning Agent, to include;
v) | Light distribution test using lux meter as well as photometer | Item | 1
vi) | Megger test of all cables including pole-to-pole megger test. Earth resistance test on all earth chambers. | Item | 1
23.9 | Verticality check on the columns using theodolites. | Item | 1
23.1 | Spare parts:
| a) 10m street lighting column with single sided arm | No. | 30
| b) 250W Solar LED Light | No. | 10
| c) 200W Solar LED Light | No. | 10
Sub Total
Total Carried Forward to Summary Page

## Bill No24
BILL OF QUANTITIES No. 24
RELOCATION AND PROPOSED NEW ROUTES FOR POWER DISTRIBUTION
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
24.1 | 11kV O/H Line Rerouting including dismantling, supply, erection, stringing, earthing, testing and commissioning complete as specified | Km | 3.1
24.2 | Allow for the rerouting of existing 415V 3-phase, 4-wire overhead distribution line | Km | 5.5
24.3 | Allow for the rerouting of existing 240V single-phase, 2-wire overhead line | Km | 2.31
24.4 | Supply, transport, and erect a 415V three-phase, 4-wire overhead low-voltage distribution line using 100 mm² all-aluminium (AA) conductors complete in every respect, including; | Km | 22.8
i)Site preparation, setting out, and verification of the line route and pole location
ii)Supply and erection of [specify type: e.g., 9 m reinforced concrete poles or galvanized steel poles], complete with foundations, cross-arms, insulators, clamps, bolts, nuts, washers, stays, struts, and all associated fittings and accessories
iii)Supply and stringing of 3-phase conductors and neutral, each 100 mm² AA, including tensioning, sagging, binding, spacers, connectors, and all fittings necessary to form a complete circuit.
iv)Installation of stays and earth stays, including stay rods, guy wires, thimbles, and turnbuckles properly anchored and tensioned
v)Provision of earthing and bonding for poles, stays, and neutral points using galvanized earth rods and 35 mm² bare copper/steel earth conductor, including testing of earth resistance.
vi)Supply and installation of line accessories such as strain and suspension insulators, connectors, binding wire, spacers, and anti-vibration devices as required
vii)Connection to existing LV network including all jointing kits, terminations, and testing
viii)Reinstatement of disturbed surfaces and site clearing upon completion
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
24.5 | Supply, transport, and construct a complete 11kV, 3-phase overhead distribution line using 75 mm² Aluminium Conductor Steel Reinforced (ACSR), including all associated works, materials, and fittings as follows | Km | 8.505
i)Site reconnaissance, route survey, setting out, and marking of pole positions along the approved alignment.
ii) Supply and erection of [e.g., 11m reinforced concrete or galvanized steel poles], including excavation, foundation construction, backfilling, compaction, and curing to the Engineer’s approval.
iii) Supply and installation of cross-arms, brackets, insulators (strain and suspension types), clamps, bolts, nuts, washers, and all associated line hardware suitable for 11kV operation
iii) Supply and stringing of 3-phase 75 mm² ACSR conductors, including sagging, tensioning, binding, installation of spacers, vibration dampers, connectors, and all necessary fittings for a complete line.
iv)Supply and installation of earth wire (if required) including all terminations, bonding, and continuity connections
v)Supply and installation of stays and struts, complete with galvanized stay rods, turnbuckles, stay wires, thimbles, and concrete anchors
vi)Provision of earthing for poles, stays, and transformer points using galvanized earth rods, 35 mm² bare copper/steel wire, clamps, and accessories; includes testing of earth resistance
Vii)Installation of anti-climbing devices, danger plates, phase plates, and pole numbering as required by utility standards
viii)Connection to existing 11kV network at both ends, including all necessary jointing kits, terminations, and jumpers.
24.6 | Allow for a sum of KES 296,000 per km for the rerouting of an existing 415V, 3-phase, 4-wire overhead low-voltage distribution line | Km | 5.5
24.7 | Supply, transport, and construct a complete 415V, 3-phase, 4-wire overhead low-voltage distribution line, including all necessary materials, labour, tools, and equipment to complete the works | Km | 5.1
24.8 | Supply, transport, and construct a complete 240 V, 2-phase, 3-wire low-voltage overhead distribution line using 100 mm² all-aluminium (AA) conductors | Km | 1.1
24.9 | Supply, transport, and construct a complete 240 V single-phase, 2-wire low-voltage overhead distribution line using 100 mm² all-aluminium (AA) conductors | Km | 2.3
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
24.1 | Supply, Installation, Testing and Commissioning of Distribution Transformers
Supply, transport, install, test, and commission oil-immersed, naturally air-cooled (ONAN), three-phase, 50 Hz, 11kV/415V-240V distribution transformers connected in Dyn11 configuration, complete with all accessories and civil/structural works necessary for full and safe operation of the following capacities;The work shall include but not be limited to;
i)Delivery of transformers complete with primary (HV) and secondary (LV) bushings, conservator tank, breather with silica gel, thermometer, oil level gauge, nameplate, earthing terminals, and drain/sampling valves.
ii)Construction of transformer foundation plinths or pole-mounted platforms, including excavation, reinforced concrete works, steel base frames, and holding-down bolts
iii)Installation of HV and LV terminations
iv)Earthing system including neutral earthing, tank earthing, and stay earthing using galvanized earth rods, conductors, clamps, and testing for earth resistance.
| v)Supply and filling of transformer oil meeting IEC/BS standards, including testing of Breakdown Voltage (BDV) before energizing |  |  |  | `
vi)Painting, labeling, and safety signage, including danger plates, phase plates, and transformer identification numbers
vii)Coordination with the power utility for switching, connection approval, and energization procedures
24.10.1 | 315kVA Transformer 11kV-415V/240V | no. | 6
24.10.2 | 200kVA Transformer 11kV-415V/240V | no. | 8
24.10.3 | 100kVA Transformer 11kV-415V/240V | no. | 1
24.11 | Carry out all necessary works for the uprating of an existing 50 kVA distribution transformer installation to a 315 kVA | No. | 3
24.12 | Supply, transport, erect, test, and commission a complete 33 kV overhead power transmission line from Galu Substation (Ukunda) to the proposed SEZ Substation, using 150 mm² Aluminium Conductor Steel Reinforced (ACSR) conductors, including all materials, labour, tools, and incidentals necessary to complete the works as per approved drawings and utility standards. | KM | 17.9
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
24.13 | Allow for KES 199,607,244 for Carry out the design, supply, installation, testing, and commissioning of a complete 33kV/11kV outdoor substation rated at 23 MVA, to be constructed on a 1-acre site within the Special Economic Zone (SEZ), in full compliance with Kenya Power (KPLC) design and construction specifications, Kenya Ports Authority (KPA) approvals, and Engineers Board of Kenya (EBK) .Allow for feeders to Resettlement area, DK1 Port and 2 Feeder Extra Unitsprofessional policies for substation works. | Lot | 1
Attendance upon KPLC Engineers
24.14 | Allow a Prime Cost Sum (P.C) of KES 14,500,000 for supervision of the project works by Kenya Power (KPLC) engineers | P.C | 1
Wayleave Acquisition and Coordination by KPLC Engineers
24.15 | Allow a sum of KES 7,000,000 to cover costs associated with Wayleave acquisition, verification, and approval by Kenya Power and Lighting Company (KPLC) Engineers in coordination with the Kenya Ports Authority (KPA) and SEZ Authority for the proposed 33kV/11kV power distribution line within the SEZ | LS | 1
Factory Acceptance Tests (FATs) for Electrical Equipments
24.16 | Allow for the Factory Acceptance Testing (FAT) of all major electrical equipment to be supplied under this Contract, including but not limited to; | LOT | 4
i | Transformers
ii | 11kVLine Disconnectors switches, Concrete Poles
iii | Circuit Breakers
iv | Conductors 11kV Line Insulators, Surge Diverters and Overhead line fittings
Training and Documentation
24.17 | Allow a Sum of KES 4,500,000 for provision of comprehensive training and documentation for the Employer’s staff and authorized representatives (including KPLC Engineers and SEZ technical personnel) on all electrical systems and equipment installed under this Contract | LS | 1
24.18 | E.O. item 24.13-24.17 for the Main contractor's overheads and profits | %
Sub Total
Total Carried Forward to Summary Page

## Bill No25
BILL OF QUANTITIES No. 25
ENVIRONMENTAL SOCIAL, HEALTH AND SAFETY MANAGEMENT AND MONITORING
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
A | Environmental Management
25.01 | Dust suppression on gravel surfaces and haul routes (bowsers/sprinklers as directed) including diversions, borrow pits, and working areas, all to the satisfaction of the Engineer and environmental regulations. | Month | 12
25.02 | Allow a sum of KES 250,000,000 per month for Erosion & sediment control: silt fences, check dams, sediment traps at drainage crossings/borrow areas. | Month | 12
25.03 | Fuel storage area: lined and bunded with 110% capacity; spill kits and drip trays. | LS | 1 |  |  | 49.5
25.04 | Portable toilets/adequate sanitation at work sites and camps; regular servicing. | Month | 12
25.05 | Hazardous waste handling: used oil/filters/grease, temporary storage in sealed containers and disposal via licensed facility. | Month | 12 |  |  | 4.5
25.06 | Non-Hazardous waste handling: used paper/foodwaste/metal, temporary storage in a designated area and disposal via licensed facility. | Month | 12
25.07 | Culvert/side drain protection: inlet/outlet rock riprap or gabions; energy dissipation to prevent scouring. | m³ | 129
25.08 | Noise and vibration control: equipment maintenance, mufflers, and daytime working near settlements. | Month | 12
A25.09 | Climate Change Mitigation Measures-in line with the Green Port Policy
| Allow sum of KES 4,550,000 for Roadside and camp greening: tree planting and caring for 3months at disturbed areas (coastal‑tolerant species). The Contractor shall give a proposal under this item and measurement and approval shall be done by the Engineer. | LS | 1
B | Occupational Health & Safety (OHS)according to OSHA, 2007
B25.01 | Provision of Personal Protective Equipment (PPE): Including boots, helmets, vests, gloves, goggles, masks, ear protection. | Month | 12 |  |  | 218.5
B25.02 | First aid kits and trained first aiders at each active work front. | Month | 12
B25.03 | Firefighting equipment: extinguishers, sand buckets; inspection and training. | Item | 1
B25.04 | Trainings and Audits on Safety
a) | Fire Safety Training | No. | 1
b) | Fire Safety Audits | No. | 1
c) | First Aid Training | No. | 2
d) | First Aid Audits | No. | 2
e) | Occupational Safety and Health(OSH) Committee Training | No. | 1
f) | Inspection and Servicing of Fire Extinguishers | No. | 2
Total Carried Forward to Next Page |  |  |  |  | 0
Total Brought Forward from Previous Page |  |  |  |  | 0
B25.05 | Work zone safety: signage, cones, barriers, lighting, and reflective tapes. | Month | 12
B25.06 | Temporary traffic control: flagmen, marshals, and temporary crossings near Schools/sensitive . | Day | 300
B25.07 | Emergency response plan: drills for spills, accidents, extreme weather, and heat stress. | Month | 12
C | Social Management
C25.01 | Allow for a prime cost sum of KShs 6,000,000.00 (six Million) for stakeholder engagement meetings (notices, venues, translation, minutes, and sign‑in sheets). | PC sum | 1
C25.02 | Allow for a prime cost sum of KShs 2,400,000.00 (Two Million four hundred thousand only) for grievance Redress Mechanism (GRM): Including establishment and operation of committees). | PC sum | 1
C25.03 | Allow for a prime cost sum of KShs 5,000,000.00 (Five Million) for HIV/AIDS & STI awareness and prevention campaign(quarterly). | PC sum | 1
C25.04 | Provide and maintain Community liaison officer (CLO) with transport/communications. | Month | 12
C25.05 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items C25.01-C25.04 above | %
D | E&S Monitoring & Staffing
D25.01 | Provide and Maintain 1No. EHS Officer (full‑time) with reporting and logistics. | Month | 12
D25.02 | Social/GBV focal person (part‑time) for grievance and GBV/SEA/SH actions. | Month | 12
D25.03 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items C25.02 above | %
D25.04 | Environmental monitoring including accredited lab fees.
a) | Water quality | Days | 50
b) | Air(PM10) | Days | 50
c) | Noise | Days | 50
d) | Effluent/waste water | Days | 12
D25.05 | Biodiversity/ecosystem monitoring near mangroves. | Days | 50
D25.06 | Monthly E&S monitoring reports with photos and corrective actions. | Month | 12
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
E | Site Rehabilitation & Demobilisation
E25.01 | Removal of temporary facilities and waste; site cleanup. | LS | 1
E25.02 | Borrow pit/quarry reinstatement and drainage; safety fencing until stabilization. | LS | 1
E25.03 | Landscaping and re‑vegetation of disturbed areas; 3‑month maintenance. | m² | 130000
E25.04 | Final E&S completion report with photographic evidence and sign‑offs. | No. | 1
F | Chance Finds & Cultural Heritage
F25.01 | Implement Chance Finds Procedure: staff training, stop‑work protocols, and notifications. | Month | 12
F25.02 | Provision for archaeological specialist/site visit if triggered. | Day | 150
F25.03 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items F25.02 above | %
G | Permits & Compliance
G25.01 | Regulatory compliance (including EIA study for the project site and statutory fees): NEMA conditions implementation, reporting, and inspections support. | Month | 12
G25.02 | Permits for all borrow pits/quarries, waste transporter contracts, and water abstraction approvals. | LS | 1
G25.03 | Percentage adjustment for profit, administration, attendance upon, overheads, etc. for Items G25.01 and G25.02 above | %
Sub Total
Total Carried Forward to Summary Page

## Summary
GRAND SUMMARY OF BILLS OF QUANTITIES
ITEM NO. | DESCRIPTION | SUB TOTAL KES
1 | Preliminaries and General | 0
4 | Site Clearance and Topsoil stripping | 0
5 | Earthworks | 0
7 | Excavation and filling for structures | 0
8 | Culverts and Drainage Works | 0
9 | Passage of Traffic | 0
10 | Gravel Wearing Course | 0
17 | Concrete Works | 0
22 | Dayworks | 0
23 | Solar Street-lighting and Installations | 0
24 | Relocation and Proposed New Routes for Power Distribution | 0
25 | Environment Social, Health and Safety Management and Monitoring | 0
| SUB -TOTAL (A) : | 0 | 0 | 0
| Contigency (10% of A) | 0
| SUB-TOTAL (B)(Sub-Total A +Contigency) | 0
| Add 16% of Sub - Total (B) for V.A.T | 0
| Grand Total carried to Form of Bid | 0

## APP-2.1
ENGINEER'S STAFF OFFICE DRAWING

## APP-2.2
APPENDIX 2.2: OFFICE FUNITURE AND OFFICE EQUIPMENT NOTE: THE WHOLE OF THIS BILL IS PROVISIONAL
Item No. | Description | Unit | Quantity | Rate | Amount
|  |  |  | KES | KES
1. FURNITURE (for the proposed Engineer's site office
1 | Executive desk 2200 x 900mm with six lockable drawers, veneer finish, hardwood edging, complete | No | 1
2 | Executive desk 1600 x 900mm with six lockable drawers, veneer finish, hardwood edging, complete | No | 3
3 | Orthopedic Mesh Chair (with lumbar support, headrest, arms) — TAPL | No | 20
4 | Mid-range padded/cushioned chairs | No | 6
5 | 2 seater Heavy duty stainless steel frame, perforated steel, with armrests | No | 1
6 | 4 seater Heavy duty stainless steel frame, perforated steel, with armrests | No | 1
7 | Lockable stationery cupboard External dimensions (typical): Height 1.2 m × Width 1.0 m × Depth 1.0 m fabricated from 20–22 gauge cold-rolled steel sheet, powder-coated finish in grey or beige | No | 1
8 | Steel filing cabinet, vertical type, overall size approximately 1.4m high x 0.45–0.50m wide x 0.60m deep, fabricated from cold-rolled steel sheet, powder-coated finish, complete with four (4) full-depth drawers mounted on heavy duty runners, each drawer suitable for A4/Legal files, fitted with central locking mechanism and supplied with two (2) keys. | No | 4
9 | Bookshelf, overall length approximately 1.2 m, depth 0.35–0.45 m, height as required to accommodate box files, fabricated in laminated MDF/plywood or equivalent hardwood frame, fitted with three (3) adjustable shelves, complete with framed sliding glass doors in aluminium/steel runners, lockable, polished/laminated finish | No | 4
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
10 | Large rectangular conference table approximately 4.0 m × 1.2 m × 0.75 m, top finished in MDF/veneer or hardwood laminate, complete with modesty panel and cable management provisions, together with sixteen (16) high/mid-back upholstered conference chairs with armrests, on swivel/fixed base as specified, finished in fabric/leatherette, lockable and polished | No | 1
11 | Office curtains, made from heavy-duty curtain fabric (polyester or polyester-cotton blend, min. 200–250 gsm), lined with plain white/cream polyester lining to reduce glare and improve durability. Curtains to be full length (floor-to-ceiling or window-sill drop as per site measurements), double-pleated, with hems neatly finished, mounted on 25–32 mm diameter powder-coated aluminium curtain rods/tracks complete with brackets, rings, end caps, runners and all necessary accessories, lock-stitch sewn | Set | 1
2. ENGINEER'S OFFICE EQUIPMENT (Ownership to revert to the Employer upon completion of contract.)
12 | Electronic scientific calculator, 12 figures | No | 6
13 | Basic Heavy duty Stapling machine Ofrex size 50 or similar with 5000 staples | No | 6
14 | Heavy duty punch and spiral binder, IBICO AG or similar approved | No | 2
15 | Pencil sharpener (desk mounted type) Mounted, with clamp / hand-crank, ABS + steel blade, anti-slip base | No | 2
16 | Heavy - duty 2 hole paper punch | No | 2
17 | Ordinary 2 hole paper punch | No | 6
18 | Occupational First Aid Kit Lockable metal box, 238 medical items | No | 2
19 | 9 kg Dry-Powder Fire Extinguisher | No | 2
20 | Filing Tray | No | 4
21 | Waste paper basket | No | 4
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
21 | Refrigerator, frost-free type, 250 litres gross capacity; with a Fridge-guard | No | 1
22 | Wall mountable Cupboard 1.08 m3 lockable | No | 2
23 | Cooker 4 plate electric cooker with oven and grill | No | 1
24 | Water dispenser: Hot and Cold | No | 1
25 | Microwave 20litres | No. | 1
26 | Electric water kettle of capacity 1.5 stainless steel or heat-resistant plastic body | No. | 1
27 | Kitchen utensil i.e. cooking pots, cutlery, plates, cups, glasses, serving spoons, trays, storage containers, dish rack, 2 No. Thermos and associated accessories | LS | 1
28 | Brand new high-performance laptops suitable for engineering and CAD applications in accordance with the Works Specifications and engineer's approval | No. | 8
29 | Portable external hard disks with storage capacity of 2TB | No. | 8
30 | Brand new desktop computer complete with monitor, keyboard, mouse, and UPS in accordance with the Specifications and engineer's approval | No. | 2
31 | Brand new multifunction office printer(A3 capability) in accordance with the Specifications and engineer's approval | No. | 1
32 | Supply, configure, and maintain foldable smartphones for Site Supervision Team (Samsung Galaxy Z Fold 7 or approved equivalent) | No. | 8
33 | Heavy-duty cross-cut paper shredder | No. | 2
34 | Air conditioner unit, medium size | No. | 5
35 | AutoCAD software (latest licensed version, 2025 or current at time of order) | No. | 7
36 | Appropriate Project Management software for the project duration including defect liability period in accordance with the Specifications and engineer's approval | No. | 6
37 | Rugged digital camera inaccordance with the specification | No. | 1
Total Carried Forward to Next Page
Total Brought Forward from Previous Page
38 | 3ftx2ft Whiteboard or PinboardWith Stand,1 Duster & 2 Markers | No. | 2
39 | Waste bin | No. | 3
40 | Plastic Chairs | No. | 5
CARRIED FORWARD TO BILL No. 1 PRELIMINARY AND GENERAL ITEMS
0

## APP-3
APPENDIX 3: Surveying Equipment NOTE: THE WHOLE OF THIS BILL IS PROVISIONAL
Item No. | Description | Unit | Quantity | Rate(KES) | Amount(KES)
ENGINEER'S SURVEY EQUIPMENT (Ownership to revert to the Employer upon completion of contract.)
1 | Hi‑Target GNSS/RTK/Differential GPS (Base + Rover) | Set | 1
2 | Total Station (Topcon ES-series) - instrument (model ES-100 recommended) | Set | 1
3 | Tripod & Tribrach (heavy-duty) | Set | 1
4 | Field Data Collector (Topcon/Android handheld) - sold separately | No. | 1
5 | Extra batteries (2) + charger | Set | 1
6 | Carrying case / hard case | Set | 1
7 | Software license (Field-to-office transfer & basic processing) | Licence | 1
8 | Automatic Level (e.g. Topcon AT‑B4) | Set | 1
9 | Handheld GPS (Garmin eTrex 32x or equivalent) | No. | 1
10 | Wooden Tripod | No. | 1
11 | Aluminium Tripod | No. | 1
12 | 3‑Metre Detail Pole / Prism Pole | No. | 1
13 | 5‑Metre Leveling Staff | No. | 2
14 | Prism set (single prism + holder + target) | No. | 1
15 | 50m Steel Tape Measure | No. | 2
16 | 30m Steel Tape Measure | No. | 2
17 | 100m Steel Tape Measure | No. | 1
18 | Measuring Wheel (12″/30cm) | No. | 1
19 | Field Book (hardcover 200 pages) | No. | 5
20 | Data Collector / Survey‑grade Tablet | No. | 1
21 | Laptop with Survey / Civil CAD Software | No. | 1
22 | Flagging Tape / Marker Paint | Roll/Can | 5
23 | Plumb Bob | No. | 2
24 | Mallet / Hammer | No. | 2
25 | Heavy duty survey umbrella | No. | 2
26 | Pangas | No. | 3
CARRIED FORWARD TO BILL No. 1: PRELIMINARY AND GENERAL ITEMS

## APP-4
APPENDIX 4: Dispute Avoidance/ Adjudication Board (DAAB)
Dispute Avoidance/ Adjudication Board (DAAB)
Allow a Prime Cost sum to cover Employer's obligation to pay DAAB
Total construction period (months) |  | 12 | months
Total construction period (Years) |  | 1 | years
Deffects notification period (months) |  | 12 | months
Number of DAAB members |  | 1 | Certified Arbitrators
Rate per Hour |  | 25000 | Kshs.
1. CONSTRUCTION PERIOD
(a). Monthly retainer fees during construction period
No. of DAAB Members | Fee (Kshs) | Total fee per month (Kshs) | Total fee for project duration (Kshs)
1 | 400000 | 400000 | 4800000
(b) Site visit
Number of sittings per year |  | 3 | times a year
Number of sittings during construction period |  | 3 | times/1 years
Number of working days per site visit |  | 5 | days
Daily allowance for site visit |  | 200000 | Kshs.
Site visit expenses per visit (air ticket, accomodatio etc) |  | 500000 | Kshs.
Total site visit fee |  | 3000000 | Kshs.
Total site visit expense |  | 1500000 | Kshs.
(c) Referrals
Assumed number of referals during construction |  | 3 | times
Total cost of referral fee |  | 3000000 | Kshs.
Total DAAB cost during construction |  | 9300000 | Kshs.
2. DNP
(a). Monthly retainer fees during DNP
Monthly allowance |  | 200000 | Kshs.
Total monthly allowance |  | 2400000 | Kshs.
Total DAAD cost during construction and DNP |  | 11700000 | Kshs.

## APP-5
APPENDIX 4: Safety Equipment NOTE: THE WHOLE OF THIS BILL IS PROVISIONAL
Item No. | Description | Unit | Quantity | Rate(KES) | Amount(KES)
1 | Safety Helmet (Hard Hat)-With chin strap | No. | 20
2 | Reflective Safety Vest (Class 2/3)-High visibility | No. | 20
3 | Safety Boots (Steel Toe)-Anti-slip, puncture resistant | Pair | 20
4 | Safety Glasses / Goggles-Impact resistant | No. | 20
5 | Protective Gloves-General purpose | Pair | 20
6 | Dust Mask / Respirator (N95 or equivalent) | No. | 3000
7 | Hearing Protection (Earplugs/Earmuffs) | No. | 500
8 | Rain Suit (Reflective Jacket & Trouser)-Waterproof | Set | 20
9 | First Aid Kit (Portable)-Per team/vehicle | No. | 6
10 | Portable Traffic Cones (Set) | Set | 10
11 | Gum Boots (PVC Waterproof Boots) | Pair | 20
CARRIED FORWARD TO BILL No. 1: PRELIMINARY AND GENERAL ITEMS